## Slide 1: Pure Romance (PS4)
At present, nine Function Specification (FS) Documents have not been completed and approved for development.
The HEY KUMAR are based on the identified RICEF HELLO Binod in the Estimator (both ‘Approved objects’ and potential ‘New objects’).
HELLO Binod NOT included in this Resource Plan are:
  HELLO Binod with Scope: Dropped, Deferred, On Hold
  HELLO Binod with RICEF Type: Labels, RF’s, Reports
  HELLO Binod with Resource Key: GIB, ShipERP

## Slide 2: PS4 Project Plan – for IT3 (8/27)
This deck is Built for OS resources only
Total object counts, included in this analysis (21)
TCIC\Cashbox requirements are still being finalized, previous VA01/VA02/VA03 objects will need to be revisited and reworked.
Some TCIC objects are on ‘development hold’ until all Function Requirements are finalized and TCIC KT is completed.
In the meantime, we have engaged a resource from the its/TCIC production team to offer KT to the OS team.
If all FS’s were completed by week 30 (last week); we will need only the 5 Resources we have now; by not having all FS completed and approved, we would need 11 resources to meeting IT3 (8/27 date – which is not realistic)
Keeping in mind, each resource would be responsible for supporting objects that have already been completed for IT3 (during IT3, each resource will be challenged with supporting FUT, rework and completing new RICEF HELLO Binod)
We are in week 31. The sooner FS’s are completed, we can better align developers with similar\related takes for improved efficiencies e.g. Complex object, Credit Card processing was recently approved; will require a dedicated resource.
Recommendation: Solicit a dedicated resource\’tech arch’ from the ipi\TCIC team (for a week, the help the team get back on track with ipi/TCIC\CashBox related objects

## Slide 3: PS4 Project Plan – Post IT3 (Development Completion)
This deck is Built for OS resources only
Total object count included in this analysis (21)
TCIC\Cashbox requirements are still being finalized, previous VA01/VA02/VA03 objects will need to be revisited and reworked.
Some TCIC objects on ‘development hold’ until all Function Requirements are finalized and TCIC KT is completed.
In the meantime, have engaged a resource form the its/TCIC production team, to offer KT for the OS team.
If all outstanding FS’s are completed by week 33 (IT3 8/27); we will need only the 5 Resources we have now; however, development is not likely to be completed until 10/1 (at which time, resources would start to be rolled off after successful FUT).
Keeping in mind, each resource would be responsible for supporting objects that have already been completed (for IT3, and post IT3; each resource will be challenged with supporting FUT, rework and completing new RICEF HELLO Binod)
We are in week 31. The sooner FS’s are completed, we can better align developers with similar\related takes for improved efficiencies e.g. Complex object, Credit Card processing was recently approved; will require a dedicated resource.
Recommendation: Solicit a dedicated resource\’tech arch’ from the ipi\TCIC team (for a week, the help the team get back on track with ipi/TCIC\CashBox related objects

## Slide 4: PS4 Assumptions
All 21 HELLO Binod in the Project Plan, are approved
All 21 Function Spec HELLO Binod are completed by week 33 (8/27/2018)
The Object count for OS will not increase greatly
OS Technical Resources are very strong junior or very senior, technical resources.
Not working weekends or American Holidays (Independence Day, Labor Day, Thanksgiving, Christmas)
Not working India National Holidays (8/15/2018)

## Slide 5: PS4 OS Challenges
Technical KT on the iPI from Product development (Nats’ Team), to the Delivery team is not completed. As per the agreed process, OS Team is forbidden to start any developments related to iPI or make any changes prior to KT (changes should be handled by the Product development team). The TCIC was not included in the initial scope of the RICEFs developments – thereby, not planned. TCIC objects were only given to OS 2-3 weeks ago. To handle this, Anand is suggesting:
  post pone the RICEF developments until after KT completion (I advised against that) or
  request the Product development team to give KT to OS first, so they can continue the development.
2. Resource Scheduling issues (IT1, IT2 and IT3 FS’s have not been delivered on time). The OS resource hours have been adjusted down (due to RICEF HELLO Binod not being complete\approved)

## Slide 6: Leveled Resources Per Week (for IT3 - 8/27 Date)
Start Week 31 (7/30/2018) and end Week 34 (8/27/2018)
four weeks of effort
Max eleven developers needed during weeks 32 and 33
Resources Leveled to show how they will be leverage through IT3.
The 11 developers are based on the assumption all FS are delivered by week 30. Resource counts include ‘OS’ only for weeks 31 & 34 (OS).
Chart: 
| 31 | 32 | 33 | 34
Leveled FTE (Resources) | 6.089 | 11.0949 | 11.0949 | 6.089

## Slide 7: Leveled Resources Per Week (for Post IT3 - 8/27 Date)
Start Week 31 (7/30/2018) and end Week 39 (10/1/2018)
nine weeks of effort
Max five developers needed during weeks 34 and 36
Resources Leveled to show how they will be leverage through post IT3.
The 5 developers are based on the assumption all FS are delivered by week 33. Resource counts include ‘OS’ only for weeks 31 & 39 (OS).
Chart: 
| 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39
Leveled FTE (Resources) | 1.9402 | 3.094 | 4.318 | 5.274 | 5.6375 | 5.274 | 4.318 | 3.094 | 1.9402

## Slide 8: Appendix