## Detailed Guideline
Guideline to Fill the Work Management Sheets
Field Name | What to Fill
Sheet 4: Skill Matrix (Update Every Month, Add new resources and delete left resources, update the actual if training provided)
Skills Required | List the skills sets required to run the service line. Expand it as much as possible
Needed | In the scale of 1 to 4 (Basic, Hands on, Extensive and SME) decide what level of knowledge is required to perform the role and responsibilities assigned to the employee
Actual | In the scale of 1 to 4 (Basic, Hands on, Extensive and SME) decide what level of knowledge the employee holds against the required level of knowledge. In case there is gap (Needed>Actual) the training must be planned and executed.
Sheet 5: Training Plan (Increamental, Don't delete previous month's record, Plan in Advance)
SN | Serial Number
Training Requirement | Mention the topic or subject or skill set on the training is required
Mode of Training | select from drop down. Either it is classroom or online or on job training
Resources Planned | write the names of the employees who requires the training. Please do not write numbers here
Training Required By Date | Put the Planned End Date, A date by which the training is supposed to end.
Training Attended By | Name of the employees/people who attended the training
Training Completion Date | Actual completion date the training ended
Effort Spent | No of days/hours
Status | As per the drop Down
Trainer Name | Name the trainer, he/she can be an Internal or an external trainer
Sheet 6: Issue Management (Increamental, Don't delete previous month's record)
Issue ID | An 8 digit alphanumeric number. Format: 1st 2 digit shall be the acronym of service line Name, 2nd 3 Digits are "IID" followed by serial number starting from 001. for e.g. DNIID117, where DN is Dot Net followed by IID, 117 is the serial number of the issue.
Issue Description | A brief description of the issue in maximum of 100 words. The description should be very précised and capable enough to provide an idea about the issue.
Raised By | Name of the person who raised the issue, it can be a team member, an employee from other Service line or department or the client or the management
Date Raised | date on which the the issue is raised in the format of DD/MM/YYYY
Internal / Client | Isssue may be either internal team issue or external may be the client or the from other service line/department
Severity | On the the scale of 1-3, where 1=Low, 2- medium and 3= High, selcet from the dropdown
Owner | A person within the team/Service line who is supposed to resolve or get the issue resolved.
Is the Issue Escalated | NO- if the issue owner resolved the issue by his/her own and YES-In case the issuse could not get resolved by the owner and he needed to go to highre level or other service line or department to get is resolved.
Escalated To | Name of the person or department/service line to whom the issue get escalated in case the issue is esclated
Current Status | Staus as on the sheet is getting updated, Every time the sheet gets updated the status may changed. Choose the right option form the drop down
Closed on | When the status of an issue reaches to closed, please mention the same date here
Issue is Recurring | If the issue has been occurred in past also or if you feel the it may occur in future thenwrite Yes else NO
Cause for Variation | Very short description of the result of investigation in
Corrective Action | Every issue must be resolved. Mention here the resolution taken against the issue in very precised manner. Maximum in 50 words.
Target Date of Completion | At the time the issue got raised the owner needs to set a target time to resolve it. The target date should be here
Actual Date of Completion | Once the target achivede means the issue got resolve fully and all measures have been taken. Put the date here
Remarks | Any remark from Owner. Very preciised. Maximum 50 words.
Sheet 7: CAM (Hw Sw Reesource) (Increamental, Don't delete previous month's record)
Resources | Name of the hardware or software. One keyboard + one Mouse + one Dektop shall be counted as one unit. The monitors should be counted seperately
Units | The unit of the resources in which it is measured eg number, GB, Meter etc
Planned Count | Quantity of resource required for the smooth operations
Actual Count | Quantity of resource actually available
Threshold capacity | The quantity of resource extra from the required. In case the Actual> Palnned
Inferences (In case Actual is less than required) | The quantity of resource lesser from the required. In case the Planned> Actual
Possible causes | A brief reason. Maximum 20 words
Actions taken to address situation | How did you managed the situaion when actual quantity of the resource was lesser than the Planned quantity. A brief.
Sheet 9: Lesson- Learnt Best Practice (Increamental, Don't delete previous month's record)
Lessons Learnt/Best Practices | Write a brief on any ideataion, creative idea or action taken in favor of the service line or the company to enrich the process or productivity. Maximum of 100 words
Benefit Realized | Any benefit realised from the action taken. Support your statement with evidence or data. Maximum 100 words
Sheet 11: Request cum Change Management (Increamental, Don't delete previous month's record)
Request No/ ID | An 5 digit alphanumeric number. Format 1st 2 digit eithe NR for new request or CR for chanfge request followed by serial number starting from 001. for eg CR072 meand change request number 72.
Type | Select either it is a change rrequest or new request
Request Description | A brief what needs to be done in maximum 100 words.
Date Received | Date on the request received
Requested By | Who requested
Priority | High, Medium or Low
Assigned to | Name of the person the request is assigned to complete
Impact Analysis | Possible impact of the change request such as delay in delivery etc
Request Status | Status while updating the sheet
Request Close Date | Date on the work got done as per request
Effort Spent | No of Hors/days to finish the work
Remarks
Sheet 12: Risk Management (Increamental, Don't delete previous month's record)
Risk Identified On | The date on the risk was identified
Risk Description | A brief description of the Risk with probale loss in maximum of 100 words. The description should be very precised and capable enough to provide an idea about the risk.
Risk Source | Probable source of the risk such as employee, the client, management, government or regulatorty bodies, Nature etc
Risk Category | Categor of the risk. It may be people risk, process risk, legal risk etc
Owner | A person who is suppose to mitigate the risk
Intial Probability | Probability of occurance of the risk while it was identified. In the scale of 1 to 5 where 1=Rare, 2=Unlikely, 3=Possible, 4=Likely, 5= almost certain
Intial Impact | Probable impact of the risk while it was identified. In the scale of 1 to 5 where 1=Negligible, 2=Minor, 3=Moderate, 4=Major, 5= catastrophic
Intial Risk Priority | Probable impact of the risk while it was identified, where impact== Probability*Impact on the scale of 1 to 4 where, 1=minor, 2= medium, 3=major, 4= Extreme
Mitigation Plan | A brief of the plan to avoid the risk. In brief max 100 words
Contigency Plan | A brief of the plan of action incase the the risk converts into an incident. In brief max 100 words
Latest Probability | Probability of occurance of the risk after mitigation plan made. In the scale of 1-5 where 1=Rare, 2=Unlikely, 3=Possible, 4=Likely, 5= almost certain
Latest Impact | Probable impact of the risk after mitigation plan made. In the scale of 1 to 5 where 1=Negligible, 2=Minor, 3=Moderate, 4=Major, 5= catastrophic
Latest Risk Priority | Probable impact of the risk after mitigation plan made, where impact== Probability*Impact on the scale of 1 to 4 where, 1=minor, 2= medium, 3=major, 4= Extreme
Status of risk | Status of the risk post the mitigation plan made, choose from the drop down, the valuesa are
Date of Status Updated
Remarks
Sheet 13: Incident Management (Increamental, Don't delete previous month's record)
Incident ID
Date of incident | Date of Incident happened
Time the incident | Time of incident happened
Affected People Department/s | List of the people/ department/ service line get affected by the incident
People Involved | List of the people were involved in taking corrective action
Nature of incident | nature of incident like man made incident, natural incident etc
Incident Description | A 100 word brief about the incident
Root Cause | Investigation report on reason of the incident
Corrective Actions | What corrective action was taken to overcome the situation
Preventive Actions | What preventive measures taken to avoid such situation in future
Effectiveness check of actions taken | Check report on the effectiveness of corrective action, there shall be a time gap to evaluate it
Name of the Loss | list of losses
Nature of Loss | Nature of the losses such as monetory loss, people loss, data loss, time loss etc
Monetary Value of Loss | total approx monetory value of the loss
SMWB Sheet Updataion Strategy
General Guideline | Do Not Edit or Change the Blue portion of the template, Pink may be edited
Skills Matrix | Update the current month resources, Left emloyees should be deleted
Training Plan | Increamental report. Do not delete previous months record while updating current month record
Issue Management | Increamental report. Do not delete previous months record while updating current month record
CAM Tracking (HW Sw) | Increamental report. Do not delete previous months record while updating current month record
Lesson Learnt Best Practices | Increamental report. Do not delete previous months record while updating current month record
Request Cum Change Management | Increamental report. Do not delete previous months record while updating current month record
Risk Management | Increamental report. Do not delete previous months record while updating current month record
Incident Management | Increamental report. Do not delete previous months record while updating current month record

## 1. Basic Information
Basic Information
Resource Name | Binod Kumar Gupta (VE 1025)
Email ID | binodkgupta@virtualemployee.com
Contact Number | 9560859222
Skype ID | ve.binodkgupta
Client Name | Jarrett Melvin
Client Location | USA
Client Start Date | 2015-02-18
Service Description | Web Application (MVC 5, Web API, Sql Server)
Last Updated on | 2018-01-02

## 4. Skill Matrix
Skill Matrix
S. No. | Skill Required | Needed | Actual
1 | AngularJS 1.5 | Hands on | Hands on
2 | AngularJS 2 & 4 | Basic | Basic
3 | NodeJS | N/A | N/A
4 | ASP.Net MVC | Hands on | Hands on
5 | ASP.Net Webform | Hands on | Hands on
6 | C# | Hands on | Hands on
7 | VB.Net | Hands on | Hands on
8 | Winforms | N/A | N/A
9 | WPF/MVVM/PRISM | N/A | N/A
10 | HTML/CSS/ Bootstrap | Basic | Basic
11 | Java Script/jQuery | Hands on | Hands on
12 | WCF, Web API, Web Service | Hands on | Hands on
13 | PMS Tools (JIRA, MS-Projects, Trello, Redmine, BaseCamp) | Hands on | Hands on
14 | Source Controls (TFS, SVN, Github) | Hands on | Hands on
15 | Testing Framework (Jasmine, Karma, Protractor, Selenium) | N/A | N/A
16 | CI/CD Tools (TeamCity, Gulp, Grunt) | N/A | N/A
17 | SQL Server | Hands on | Hands on
18 | MongoDb | N/A | N/A
19 | Oracle | Hands on | Hands on
20 | MySQL | Basic | Basic
21 | PhotoShop | N/A | N/A
22 | Dream Viewer | N/A | N/A

## 5. Training Requirement
Training Requirement
Ratings (1-5)
Sno | Skills | Existing Rating | Required Rating
1 | Nodejs | 0 | 0
2 | Angular2 | 3 | 3
3 | MongoDB | 0 | 0

## 6. Issue Management
Issue Management
S. No | Issue ID | Issue Description | Raised By | Date Raised | Internal / Client | Severity | Owner | Is the Issue Escalated | Escalated To | Current Status | Closed on | Issue is Recurring | Cause for Variation | Corrective Action | Target Date of Completion | Actual Date of Completion | Remarks
1 | 1 | Senior Developer resigned | Deepak Saini | 2017-04-03 | Harald Bacik | High | Deepak Saini | No | Arvind Kumar (PL) | Closed | 2017-04-14 | No | Resource resigned | Assign another resource to client for KT | 2017-05-06 | 2017-05-06 | Gaurav Bhola (Sr. Developer) resigned from his post.
2 | 2 | Project work flow was not streamlined or defined. The client does not wait for documentation and we required to complete the strict deadline. And issues happened in between. | Ravi S Pandey | 2017-07-03 | Client | High | Nitin Rohilla | No |  | Closed | 2017-07-07 | Yes | Guideline and project plan and process not shared by the client and Team joined project mid-way. | Discussed with client to setup process | 2017-07-10 | 2017-07-10 | This led to conflicts with in the project related to work delivered. In the past this has happened that after releasing a task, client has reported that the task was wrong. This happened due to no documentation of the task asssigned that we can cross verify.
3 | 3 | Uninformed late coming for work: The resources had been warned earlier but still the late coming and that too uninformed was going on. | Deepak Saini, Nitin Rohilla | 2017-09-27 | Internal | High | Shobhit aggarwal | Yes | Arvind Kumar (PL) | Closed | 2017-09-28 | No | when the late coming is planned in advance why not the resources inform the lead so we can sort out the situation | Discussion with the resource and circulate the message to the whole team | 2017-09-28 | 2017-09-28 | This reflected the casual approach of resources to work. This risk gets to even higher ground when the client project has started off and everyone expects utmost dedication and involvement of resource in work

## 7. CAM Tracking (Hw Sw)
CAM - for Hardware & Software only
Note: Include all the number/versions of sofwares and hardwares which installed on your system and not mentioned in this list.
S. No. | Resources | Units (No.)
1 | Windows | Win 8.1
2 | Visual Studio | VS 2013, VS 2015
3 | SQL Server | 2014
4 | MS Office | Yes
5 | Open Office | Yes
6 | Monitor | 1
7 | CPU | 1
8 | Keyboard | 1
9 | Mouse | 1
10 | Headphones | 1
11 | Web Cam | 1

## 10Lessons Learnt-Best Practices
Lessons Learnt - Best Practices
S.No. | Lessons Learnt/Best Practices | Benefit Realized
1 | No verbal tasks to be taken up from the client | In case of any conflict, we can always refer to the documented version of the task. In case developer loose focus on the actual task, he can refer the document. Also when there is conflict arise when client report that the wrong work has been delivered, we can always go back to the document.
2 | Follow a set agreed process for the work delilvery | This way the work to be delivered stays in check at all times and contingency plans can be applied on time. The client expectations remain very clear to every member of the project and argument window gets closed to a great extent.
3 | Give enough importance to communication skills of new hire | Good communication eliminates the issue when client interviews happen and resources are not able to understand and respond in a better way. This result in loss of lead even when the resources are well equipped with technical skills asked by the client.

## 12. Request cum Change MGMT
Request Cum Change Management
Sl No | Request No/ ID | Linked New request ID (Only For Change Request) | Date Received |  | Project Name | Type | Request Description | Requested By | Priority | Assigned to | Planned Effort Hrs. | Effort Spent | Impact Analysis | Request Status | Request Start Date | Request Close Date | Remarks
716 | JM/BG-0716 |  | 2018-07-02 | Jarrett Melvin | Freece | New Request | 1593. Evaluations / Tests seem to randomly un check questions already answered as you answer others down lower on the evaluations | Jarrett Melvin | Low | Binod Kumar Gupta | 8 | 8 |  | Open | 2018-07-02 | 2018-07-04
717 | JM/BG-0717 |  | 2018-07-02 | Jarrett Melvin | Freece | New Request | 1595. After purchasing a membership, the users cache needs to be cleared and the entire page needs to reload so that the header and other items on the page reflect the membership | Jarrett Melvin | Low | Binod Kumar Gupta | 5 | 5 |  | Closed | 2018-07-03 | 2018-07-03
718 | JM/BG-0718 |  | 2018-07-03 | Jarrett Melvin | Freece | New Request | Testing and Merge branches | Jarrett Melvin | Low | Binod Kumar Gupta | 8 | 8 |  | Closed | 2018-07-03 | 2018-07-04
719 | JM/BG-0719 |  | 2018-07-03 | Jarrett Melvin | Freece | New Request | Modify code for membership | Jarrett Melvin | Low | Binod Kumar Gupta | 3 | 4 |  | Closed | 2018-07-05 | 2018-07-05
720 | JM/BG-0720 |  | 2018-07-03 | Jarrett Melvin | Freece | New Request | Testing and Merge branches | Jarrett Melvin | Low | Binod Kumar Gupta | 4 | 4 |  | Closed | 2018-07-05 | 2018-07-05
721 | JM/BG-0721 |  | 2018-07-05 | Jarrett Melvin | Freece | New Request | 1595. Auto Renew box on the Membership purchase does not work. it leaves auto renew set to on even if it is turned off | Jarrett Melvin | Low | Binod Kumar Gupta | 3 | 3 |  | Closed | 2018-07-06 | 2018-07-06
722 | JM/BG-0722 |  | 2018-07-05 | Jarrett Melvin | Freece | New Request | 1599. After paying for a membership it needs to take them to a payment confirmation page. | Jarrett Melvin | Low | Binod Kumar Gupta | 2 | 2 |  | Closed | 2018-07-06 | 2018-07-06
723 | JM/BG-0723 |  | 2018-07-05 | Jarrett Melvin | Freece | New Request | Testing and Merge branches | Jarrett Melvin | Low | Binod Kumar Gupta | 4 | 4 |  | Closed | 2018-07-06 | 2018-07-06
724 | JM/BG-0724 |  | 2018-07-06 | Jarrett Melvin | Freece | New Request | 1599. After paying for a membership it needs to take them to a payment confirmation page | Jarrett Melvin | Low | Binod Kumar Gupta | 4 | 4 |  | Closed | 2018-07-09 | 2018-07-09
725 | JM/BG-0725 |  | 2018-07-07 | Jarrett Melvin | Freece | New Request | 195. Auto Renew box on the Membership purchase does not work. it leaves auto renew set to on even if it is turned off | Jarrett Melvin | Low | Binod Kumar Gupta | 4 | 4 |  | Closed | 2018-07-09 | 2018-07-09
726 | JM/BG-0726 |  | 2018-07-07 | Jarrett Melvin | Freece | New Request | After filling out eval when you click submit the eval errors out | Jarrett Melvin | Low | Binod Kumar Gupta | 8 | 8 |  | Closed | 2018-07-09 | 2018-07-10
727 | JM/BG-0727 |  | 2018-07-07 | Jarrett Melvin | Freece | New Request | Manual Testing and Analysis | Jarrett Melvin | Low | Binod Kumar Gupta | 8 | 8 |  | Closed | 2018-07-11 | 2018-07-12
728 | JM/BG-0728 |  | 2018-07-07 | Jarrett Melvin | Freece | New Request | Merge code with Dev branch | Jarrett Melvin | Low | Binod Kumar Gupta | 8 | 8 |  | Closed | 2018-07-12 | 2018-07-12
729 | JM/BG-0729 |  | 2018-07-07 | Jarrett Melvin | Freece | New Request | 1602. Create a page available to Administrators or better with buttons to clear cache | Jarrett Melvin | Low | Binod Kumar Gupta | 5 | 5 |  | Closed | 2018-07-13 | 2018-07-13
730 | JM/BG-0730 |  | 2018-07-07 | Jarrett Melvin | Freece | New Request | Merge code with branch | Jarrett Melvin | Low | Binod Kumar Gupta | 3 | 3 |  | Closed | 2018-07-13 | 2018-07-13
731 | JM/BG-0731 |  | 2018-07-07 | Jarrett Melvin | Freece | New Request | 719. Group Account Curriculum Tracking | Jarrett Melvin | Low | Binod Kumar Gupta | 3 | 3 |  | Closed | 2018-07-16 | 2018-07-17
732 | JM/BG-0732 |  | 2018-07-07 | Jarrett Melvin | Freece | New Request | Merge code with branch | Jarrett Melvin | Low | Binod Kumar Gupta | 5 | 5 |  | Closed | 2018-07-16 | 2018-07-17
733 | JM/BG-0733 |  | 2018-07-10 | Jarrett Melvin | Freece | New Request | 1609. On Live Events Registration Confirmation, Event Details Page ect.. when you select a handout to download it should open in a new tab | Jarrett Melvin | Low | Binod Kumar Gupta | 3 | 3 |  | Closed | 2018-07-19 | 2018-07-19
734 | JM/BG-0734 |  | 2018-07-10 | Jarrett Melvin | Freece | New Request | 1612. Add ability to set date and any user that has not updated their account since that date will be forced to update their profile. | Jarrett Melvin | Low | Binod Kumar Gupta | 2 | 2 |  | Closed | 2018-07-19 | 2018-07-19
735 | JM/BG-0735 |  | 2018-07-10 | Jarrett Melvin | Freece | New Request | 1604. Facebook Share CE Credit. Should say I just completed "Program Title" at freeCE.com | Jarrett Melvin | Low | Binod Kumar Gupta | 2 | 2 |  | Closed | 2018-07-19 | 2018-07-19
736 | JM/BG-0736 |  | 2018-07-10 | Jarrett Melvin | Freece | New Request | Merge code with branch | Jarrett Melvin | Low | Binod Kumar Gupta | 2 | 2 |  | Closed | 2018-07-19 | 2018-07-19
737 | JM/BG-0737 |  | 2018-07-10 | Jarrett Melvin | Freece | New Request | 1608. Review Services for cache managment. Ensure that updates and edits throughout the site are refreshing/clearing old cache so new data appears. | Jarrett Melvin | Low | Binod Kumar Gupta | 2 | 2 |  | Closed | 2018-07-20 | 2018-07-20
738 | JM/BG-0738 |  | 2018-07-10 | Jarrett Melvin | Freece | New Request | 1604. Facebook Share CE Credit. Should say I just completed "Program Title" at freeCE.com. | Jarrett Melvin | Low | Binod Kumar Gupta | 2 | 2 |  | Closed | 2018-07-20 | 2018-07-20
739 | JM/BG-0739 |  | 2018-07-10 | Jarrett Melvin | Freece | New Request | Merge code with branch | Jarrett Melvin | Low | Binod Kumar Gupta | 3 | 4 |  | Closed | 2018-07-20 | 2018-07-20
740 | JM/BG-0740 |  | 2018-07-10 | Jarrett Melvin | Freece | New Request | 1621: Add form validation if there is a limit so the users will know why form is not working… | Jarrett Melvin | Low | Binod Kumar Gupta | 4 | 4 |  | Closed | 2018-07-23 | 2018-07-23
741 | JM/BG-0741 |  | 2018-07-16 | Jarrett Melvin | Freece | New Request | 1625: Still blank for me…..​ | Jarrett Melvin | Low | Binod Kumar Gupta | 4 | 4 |  | Closed | 2018-07-23 | 2018-07-23
742 | JM/BG-0742 |  | 2018-07-16 | Jarrett Melvin | Freece | New Request | 1621: Add form validation if there is a limit so the users will know why form is not working… Change pattern | Jarrett Melvin | Low | Binod Kumar Gupta | 4 | 4 |  | Closed | 2018-07-24 | 2018-07-24
743 | JM/BG-0743 |  | 2018-07-16 | Jarrett Melvin | Freece | New Request | 1625. July Calendar showing blank for some users? | Jarrett Melvin | Low | Binod Kumar Gupta | 1 | 2 |  | Closed | 2018-07-25 | 2018-07-25
744 | JM/BG-0744 |  | 2018-07-20 | Jarrett Melvin | Freece | New Request | 1618. On a Test/Eval users must answer all questions | Jarrett Melvin | Low | Binod Kumar Gupta | 1 | 1 |  | Closed | 2018-07-25 | 2018-07-25
745 | JM/BG-0745 |  | 2018-07-20 | Jarrett Melvin | Freece | New Request | Performance testing of home study and webcast | Jarrett Melvin | Low | Binod Kumar Gupta | 1 | 1 |  | Closed | 2018-07-25 | 2018-07-25
746 | JM/BG-0746 |  | 2018-07-20 | Jarrett Melvin | Freece | New Request | Merge code with branch | Jarrett Melvin | Low | Binod Kumar Gupta | 4 | 4 |  | Closed | 2018-07-25 | 2018-07-25
747 | JM/BG-0747 |  | 2018-07-20 | Jarrett Melvin | Freece | New Request | 1618. On a Test/Eval users must answer all questions | Jarrett Melvin | Low | Binod Kumar Gupta | 4 | 4 |  | Closed | 2018-07-26 | 2018-07-26
748 | JM/BG-0748 |  | 2018-07-20 | Jarrett Melvin | Freece | New Request | 1634. Create Service that will allow the old admin section to manage/clear all of the different cache on the site. | Jarrett Melvin | Low | Binod Kumar Gupta | 4 | 4 |  | Closed | 2018-07-26 | 2018-07-26
749 | JM/BG-0749 |  | 2018-07-20 | Jarrett Melvin | Freece | New Request | Merge code with branch | Jarrett Melvin | Low | Binod Kumar Gupta | 4 | 4 |  | Closed | 2018-07-26 | 2018-07-26
750 | JM/BG-0750 |  | 2018-07-20 | Jarrett Melvin | Freece | New Request | 1634. Create Service that will allow the old admin section to manage/clear all of the different cache on the site. | Jarrett Melvin | Low | Binod Kumar Gupta | 4 | 4 |  | Closed | 2018-07-28 | 2018-07-30
751 | JM/BG-0751 |  | 2018-07-20 | Jarrett Melvin | Freece | New Request | Merge code with branch | Jarrett Melvin | Low | Binod Kumar Gupta | 4 | 4 |  | Closed | 2018-07-28 | 2018-07-28
752 | JM/BG-0752 |  | 2018-07-20 | Jarrett Melvin | Freece | New Request | Testing Client list from mail attachment. | Jarrett Melvin | Low | Binod Kumar Gupta | 4 | 4 |  | Closed | 2018-07-30 | 2018-07-30
753 | JM/BG-0753 |  | 2018-07-30 | Jarrett Melvin | Freece | New Request | 1639. Account Activation Required nothing happens when click resend confirmation | Jarrett Melvin | Low | Binod Kumar Gupta | 8 | 8 |  | Closed | 2018-07-31 | 2018-07-31

## 13. Risk Register
Date identified on | Risk Description |  | Risk Source | Risk Category | Owner | Initial |  |  | Mitigation Plan | Contingency Plan | Latest |  |  | Status of Risk | Date of Status Updated | Remarks
|  | Possible Impact (Cost/Schedule/Quality) |  |  |  | Probability | Impact | Risk Priority |  |  | Probability | Impact | Risk Priority
2017-04-03 | Sudden resination by Sr. Team member |  | .net team | Technological | TL/HR | 3=Possible | 3=Moderate | 2= Medium | Start KT with another developer |  | 1=Rare | 1=Negligible | 1=Minor | closed | 2017-05-06

## 14. Incident Report
Incident ID | Date of incident | Time the incident | Affected People Department/s | People Involved | Incident Category | Incident Description | Root Cause | Corrective Actions | Effectiveness check of actions taken | Name of the Loss | Nature of Loss | Approx. Monetary Value
1 | 2017-09-11 | 12:30 | Mahesh Verma | 1 | Health and Safety Incidents • Physical Security Incidents | Mahesh Met with an accident and unable to come office for 2-3 weeks | Vehicle Accident | Informed to client & Checked with client if any urgent work is affected and offered replacement resource during his absence | Client denied to take the replacement as he have to give 2-3 weeks training to new resource for work on his environment & project as well | Service Affected | Accident
2 | 2017-10-10 | 11:00 | Shivendra Shukla | 1 | Technological Incident | Visual Studio 2017 Hang & crashed when try to connect with the client's TFS because project uses some references of visual studio 2013 & visual studio 2015 and in Shivendra's system both version of visual studio were not installed. So due to this project always hang while running in VS 2017. | Project uses some references of Visual Studio 2015 & 2013 and these versions were not installed on Shivendra's System | Informed to client & IT - Dept as well | Provide him another system for the time being | Service Affected | technological |  | resolved on 24 Oct 2017