## Sheet1
<1000034>
Project Name:File Harmonizer
Start Date: 1//1/2018
Tools and technology
1. Asp Net MVC 6.0 or Core 2.0
2. C-Sharp (c#) 7.1
3. SqlServer 2016
4. Bootstrap 4.0
5. Jquery
6. Nunit, selenium and rhino for Test cases
7. Plate form: Window
8. IIS for hosting
9. Office 2013
Note: Use 3rd party dll for tranfer flat file in different format,
archive and find/replace
Project Architecture
>> N-Layer Architecture
1 | Core Laye | Hold all propertie class
2 | Data Layer | Hold all activity with DB
3 | Business Layer | Hold all business logics
4 | UI Layer | Hold all User interface
5 | TestCase | Hold all unit and moq test
Note: These all are separte class library project in single solutions.
Tentive project time for project according to primilrarly document
Start Date | Module Name | Requirement | E.C. date | C. Date | Remark
Week 1 | 12 Nov to 16 Nov
2018-01-11 | Functional Desing | Create document | 2018-01-11 |  | Revison to added after kickoff meeting
2018-12-11 | DataBase Desing | Database desing and create table/SP/Fun/View/Index - Initial Tables with table maintenance: Sector, Industry, Category | 13/11/2018
13/11/2018 | Website layout | Create project and all layers. Also create screen as HTML View. - Screen: Home, Sign In, Start My Free Month,Reactive - Finalized Screen Flow - Sceen Will need to be designed for both end users and in-house FH Website Support team | 16/11/2018
13/11/2018 | Develop function | Create method and mapping with DB - Function Module\Method: create Filter and Template from Source File - Have alignment with Database and Web designers on field table-field names - Have alignment with Database and Web designers on process flow and user-interaction flow | 16/11/2018
Week 2 | 19 Nov to 23 Nov
19/11/2018 | Database design | Database Design and Table creation - Initial Tables with Table Maintenance Screen: Filter Identification, Harmonization Filter and Templates - Work with Developer to programmatically update Table Field values for Filter and Templates | 19/11/2018
20/11/2018 | Website Layout | Website Layout and Flow - Screens: Partners, Harmonization - Introduce functionality for drag-and-drop, double-clicking, etc - Working with Developer to start integrating Filter Tag (drag-n-drop) Logic | 23/11/2018
21/11/2018 | Development & Unit Testing | Development & Unit Testing - Work with Database Designer and Web Designer to incorporate fields from the Create Function Module\Method (Filter and Template) - Develop Function Module\Method: to use a Filter to Harmonize all files in a Folder | 23/11/2018
Week 3 | 26 Nov to 30 Nov
26/11/2018 | Database designe | Database Design and Table creation -Initial Tables with Table Maintenance Screen: Tags, Business Partner Validation Period, User Validation, xREF Personal# and Address#, Last Used By and simultaneous usage sign-in -Work with Developer to programmatically update Table Field values for Filter and Harmonization, Tags -Work with Developer and Web Designer to consume\use the Database Table Values -Work with the Developer to design user password table with strong Hash Tag algorithm | 27/11/2018
27/11/2018 | Website Layout | Website Layout and Flow - Screens: Documentation, add other Desired Screens i.e. About, Contact, Pricing, Products, etc - Introduce functionality for drag-and-drop, double-clicking, etc - Working with Developer to start integrating Filter Tag (drag-n-drop) Logic | 29/11/2018
29/11/2018 | Development & Unit Testing | Development & Unit Testing - Work with Database Designer and Web Designer to incorporate fields from the Harmonize Function Module\Method (Filter all files in a Folder) - Unit Test Function Module\Method: create Filter and Template from Source File - Unit Test Function Module\Method: use Filter to Harmonize Files in Folder | 30/11/2018
Week 4 | 3 Dec to 7 Dec
2018-03-12 | Testing of basic funtions | Testing of basic funtionality
2018-04-12 | Database desing | Database Design and Table creation - Initial Tables with Table Maintenance Screen: Address Information, Personal Information, User Password, Business Partner Information, Personal Values to Share, Personal Sectors - Finalize Database Schema, make sure data normalize is done, optimize Database indexes, etc. | 2018-05-12
2018-06-12 | Website Layout | Screens: finalize Documentation, add necessary sub-screens per Database and Developer requirements | 2018-07-12
2018-06-12 | Development and Unit Testing | Development & Unit Testing -Work with Database Designer and Web Designer to trap and code for unforeseen errors -Add code to ensure data validation -Test the development for Performance for high volume of files in a folder and multiple file types | 2018-07-12